## Weekly Tracker
Week | Priority | Asset | Category | Scope | Original (USD) | Original (ZAR) | ZAR→USD @18.5 | Additionals (USD) | Planned Total (USD)
1 | 1 | M01 | Mixer | Repairs + panel beating/paint (parallel) | 2356 | 780.72 | 42.2 | 0 | 2398.2
2 | 2 | M11 | Mixer | Repairs + panel beating/paint (parallel) | 4118 | 0 | 0 | 680 | 4798
3 | 3 | Dropsides | Fleet | Tyres/lights/cluster parts + fixes | 42 | 30101.95 | 1627.13 | 1820 | 3489.13
4 | 4 | NP300 | Fleet | Injectors + stabiliser arm (right bottom) | 1720 | 0 | 0 | 600 | 2320
5 | 5 | Ford T6 | Fleet | Injectors/pump/rail/starter (ZAR quote) | 0 | 63613.88 | 3438.59 | 0 | 3438.59
6 | 6 | M08 | Mixer | Full mechanical/hydraulic/brake package | 9191.61 | 21225 | 1147.3 | 0 | 10338.91
7 | 7 | M14 | Mixer | Repairs + brake shoes + electrics | 1386 | 9960.7 | 538.42 | 680 | 2604.42
8 | 8 | M15 | Mixer | Drum roller bearing + ball joints + service kit | 1200 | 780.72 | 42.2 | 1400 | 2642.2
8 | 9 | M02 | Mixer | Repairs + cab/brakes/wipers/markers (from update) | 1795 | 780.72 | 42.2 | 2380 | 4217.2
9 | 10 | M07 | Mixer | Windscreen/turbo/cables/brake lining (from update) | 726 | 780.72 | 42.2 | 1595 | 2363.2
9 | 11 | M13 | Mixer | Service kit + compressor belt/alternator/handbrake | 265 | 4138.29 | 223.69 | 680 | 1168.69
9 | 12 | M16 | Mixer | Sump welding/locks/washdown/shute bolts | 691 | 780.72 | 42.2 | 1175 | 1908.2
10 | 13 | HOWO Tipper | Fleet | Hydraulic tank + drums + brakes + welding | 1445 | 0 | 0 | 1230 | 2675
10 | 14 | MAN Tipper | Fleet | Tower + electrical wiring | 600 | 0 | 0 | 0 | 600
10 | 15 | XCMG Loader | Plant | Wheel studs + bucket pins/bushes | 1645 | 0 | 0 | 0 | 1645
10 | 16 | Toyota GD6 AFX | Fleet | Stabiliser arm top both sides | 180 | 0 | 0 | 0 | 180
10 | 17 | Static Pumps | Plant | Rubber piston + actuator/hydraulic pipe (pending quote) | 0 | 0 | 0 | 690 | 690
10 | 18 | M04 | Mixer | Minor repairs & compliance | 1266 | 780.72 | 42.2 | 0 | 1308.2
10 | 19 | M05 | Mixer | Minor repairs & compliance | 826 | 0 | 0 | 0 | 826
|  | TOTALS |  |  | 29452.61 | 133724.14 | 7228.33 | 12930 | 49610.94

## Summary
Approved FX Rate (ZAR→USD) | 18.5
Original Totals (USD) | 29452.61
Original Totals (ZAR) | 133724.14
ZAR Converted to USD | 7228.33
Additionals (USD) | 14970
GRAND TOTAL (USD) | 51650.94

## Weekly Risk Heat Map
Week | Overall Risk | Safety | Compliance | Production | Financial | Reputation
1 | HIGH | HIGH | HIGH | HIGH | MEDIUM | MEDIUM
2 | HIGH | HIGH | HIGH | HIGH | MEDIUM | MEDIUM
3 | HIGH | HIGH | MEDIUM | HIGH | MEDIUM | LOW
4 | HIGH | HIGH | MEDIUM | HIGH | MEDIUM | LOW
5 | MEDIUM | MEDIUM | MEDIUM | MEDIUM | MEDIUM | LOW
6 | MEDIUM | MEDIUM | MEDIUM | MEDIUM | MEDIUM | LOW
7 | MEDIUM | MEDIUM | LOW | MEDIUM | MEDIUM | LOW
8 | MEDIUM | MEDIUM | LOW | MEDIUM | MEDIUM | LOW
9 | LOW-MEDIUM | LOW | LOW | MEDIUM | LOW | LOW
10 | LOW | LOW | LOW | LOW | LOW | LOW

## Cashflow vs Risk
Week | Planned Cashflow USD | Overall Risk Level
1 | 3900 | HIGH
2 | 3900 | HIGH
3 | 3250 | HIGH
4 | 3250 | HIGH
5 | 4950 | MEDIUM
6 | 4950 | MEDIUM
7 | 5500 | MEDIUM
8 | 5500 | MEDIUM
9 | 4750 | LOW-MEDIUM
10 | 4750 | LOW

## Risk Register
Risk ID | Week | Asset(s) | Risk Description | Risk Category | Likelihood | Impact | Risk Rating | Mitigation | Owner | Status
R1 | 1–2 | M01, M11, HOWO | Brake / structural failure during operation | Safety | High | High | High | Parallel repairs + QA sign-off | Engineering Manager | Open
R2 | 3–4 | Dropsides | Non-compliance leading to road prohibition | Compliance | High | High | High | Pre-inspection & spares readiness | Fleet Manager | Open
R3 | 5–6 | Ford T6 | Fuel system failure causing extended downtime | Operational | Medium | High | High | Injector testing & staged payments | Workshop Manager | Open
R4 | 7 | M08 | Scope creep during overhaul | Financial | Medium | Medium | Medium | Scope freeze & mid-week inspection | Engineering Manager | Open
R5 | 8 | XCMG Loader | Incorrect parts fitment | Operational | Low | Medium | Low | Pre-fit checks | Plant Supervisor | Open