## Monthly Cashflow
Fourways Group – Maintenance Monthly Cashflow (USD) – 2026 Plan (incl. Concrete Backlog)
Month | Planned plant spares (from registers) | Fleet & mobile equipment PM (estimate) | Generator routine servicing (estimate) | Condition monitoring (estimate) | Training/tools/CMMS-AI ops (estimate) | Concrete Backlog Execution (USD) | Total (USD) | Approx Weekly (USD) | Approx Daily (USD)
Jan | 12519.1 | 24985.84 | 715 | 0 | 750 | 6778.49 | 45748.43 | 10565.46 | 1759.56
Feb | 12519.1 | 24985.84 | 715 | 750 | 500 | 19567.92 | 59037.86 | 13634.61 | 2270.69
Mar | 22762 | 46127.7 | 715 | 0 | 250 | 25304.53 | 95159.23 | 21976.73 | 3659.97
Apr | 12519.1 | 24985.84 | 715 | 0 | 111.11 | 0 | 38331.05 | 8852.44 | 1474.27
May | 12519.1 | 24985.84 | 715 | 750 | 111.11 | 0 | 39081.05 | 9025.65 | 1503.12
Jun | 40971.6 | 46127.7 | 715 | 0 | 111.11 | 0 | 87925.41 | 20306.1 | 3381.75
Jul | 12519.1 | 24985.84 | 715 | 0 | 111.11 | 0 | 38331.05 | 8852.44 | 1474.27
Aug | 12519.1 | 24985.84 | 715 | 750 | 111.11 | 0 | 39081.05 | 9025.65 | 1503.12
Sep | 22762 | 46127.7 | 715 | 0 | 111.11 | 0 | 69715.81 | 16100.65 | 2681.38
Oct | 12519.1 | 24985.84 | 715 | 0 | 111.11 | 0 | 38331.05 | 8852.44 | 1474.27
Nov | 12519.1 | 24985.84 | 715 | 750 | 111.11 | 0 | 39081.05 | 9025.65 | 1503.12
Dec | 40971.6 | 46127.7 | 715 | 0 | 111.11 | 0 | 87925.41 | 20306.1 | 3381.75
TOTAL | 227620 | 384397.52 | 8580 | 3000 | 2499.99 | 51650.94 | 677748.45 | 156523.92 | 26067.27

## Backlog Weekly (Start 19 Jan)
Week | Start | End | Planned Total (USD) | Notes
1 | 2026-01-19 | 2026-01-25 | 2496.81
2 | 2026-01-26 | 2026-02-01 | 4995.29
3 | 2026-02-02 | 2026-02-08 | 3632.6
4 | 2026-02-09 | 2026-02-15 | 2415.4
5 | 2026-02-16 | 2026-02-22 | 3579.98
6 | 2026-02-23 | 2026-03-01 | 10764.05
7 | 2026-03-02 | 2026-03-08 | 2711.51
8 | 2026-03-09 | 2026-03-15 | 7141.46
9 | 2026-03-16 | 2026-03-22 | 5663.79
10 | 2026-03-23 | 2026-03-29 | 8250.04

## Assumptions
Line item | Annual (USD) | Allocation logic (high-level)
Routine maintenance (all operations) | 626097.54 | Monthly view based on planned shutdown months + quarterly CBM + steady servicing.
Concrete backlog execution | 51650.94 | 10-week execution plan starting 2026-01-19; weekly totals rolled into Jan–Mar.
Notes |  | This is a planning cashflow. Actuals should update weekly via Telegram/CMMS uploads (invoices, GRNs, issues, job cards).